## Sheet1
№ | From Date | To Date | Page | To Do | Note | Completed
1 | 2022-04-18 | 2022-04-20 | Create Collection | - create new collection | Frontend, Backend, Contract | Testing
2 |  |  | Create NFT | - create/mint NFT item | Frontend, Backend, Contract | Testing
3 | 2022-04-21 |  | My NFTs | - set payment token when creating sale or timed auction | Frontend | In Progress
4 |  |  | All Pages | - display nft and collection name, price, images on all pages |  | Pending
5 | 2022-04-22 |  | Home | - all components |  | Pending
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50