## Sheet1
№ | From Date | To Date | Page | To Do | Note | Completed
1 | 2022-04-18 | 2022-04-20 | Create Collection | - create new collection | Frontend, Backend, Contract | Completed
2 |  |  | Create NFT | - create/mint NFT item | Frontend, Backend, Contract | Completed
| 2022-04-21 | 2022-04-22 | All Pages | - create "Collections" and "My Collections" pages | Frontend, Backend, Moralis | Completed
|  |  | Create Collection | - create "Collection Detail" page | Frontend, Backend, Moralis | Completed
|  |  | Create NFT | - create NFT Detail page | Frontend, Backend, Contract, Moralis | Completed
|  |  | All Pages | - set payment token when creating sale or timed auction | Frontend, Backend, Moralis | Completed
|  |  | All Pages | - display nft and collection name, price, images on all pages | Frontend, Backend, Moralis | Completed
|  |  | Home | - homepage items image gallery | Frontend, Backend, Moralis | Pending
|  |  | Item Detail | - api issues not showing correct bids sometimes | Frontend, Backend | Pending
|  |  | All Pages | - auction need to show cancel auction for creators and place a bid for others
|  |  | Item Detail | - history needs to be added too
|  |  | Item Detail | - collections in item details (not able to click) - we need to see collections set for users
|  |  | Author | - we need to be allowed to see other user profile and collections
|  |  | All Pages | - like NFTs
|  |  | All Pages | - following user